## Sheet1
MatchMate Modulewise Timelines
Modules | Tasks | Timeline
Architecture & Setup | Define tech stack
cloud setup
CI/CD pipeline
code repo structure
Figma mockups
Design & Wireframes | Figma mockups (continued)
design system
user flows
User Onboarding & Identity | Signup/login
OTP based login
KYC setup (image and video)
Basic ID verification
Guardians access
Profile & Preferences | Profile creation (bio, photos, lifestyle, preferences)
Privacy controls
Matching Engine | Build preference-based matching v1
configure search & filters
Chat & Communication | Develop double-like chat unlock
in-app masked calls
Safety Features | Report/block functionality
moderation hooks
Admin Console v1 | Develop KYC queue
moderation dashboard
abuse detection pipeline
Payments Integration | Integrate UPI/cards/wallets
setup GST invoicing
Analytics & Monitoring | Set up DAU/WAU dashboards
fraud checks
error monitoring
Social Presence Module | OAuth linking
trust scoring
dashboard of derived scores
Psychology Module | Implement questionnaires
scoring service
explainable outputs
Financial Module | Finance self-report
payroll/AA verification
badges
Concierge Services | Human matchmaker workflows
family group calls
background checks
Testing whole environment and bug fixes
Beta Launch | Deploy to production for limited geography, monitor user feedback